DATE March 21, 2019

PARTICIPATION HOUSE - STATUS REPORT

| Project Name: | Participation House |
| --- | --- |
| Prepared By: | Participation House Project Managers |
| Subject: | Status Report |
| Period Ending: | March 22, 2019 |
| Self-Assessment: | Green |

KEY POINTS

- There are 2 project managers: Sydney Mensen and Teresa Turnbull. - Progress thus far includes completion of all required PM documents; review and finalization need to be done. - Lists of recruitment and marketing strategies need to be finalized and uploaded to Teams. - Presentation and final report need to be completed.

PRIORITY

- Presentation needs attention from both project managers. - The recruitment and marketing strategies lists need to be completed by both project managers and attached to Microsoft Teams. - Final report with all documents for sponsor needs to be compiled.

MILESTONES

- All required PM documents have been completed. - Final meeting, confirming deliverables have been met, completed. Participation House Deliverables: TO DO; PROGRESS; DUE DATE. Organize final meeting with project sponsor; Completed; Mar 15/19. Organize final presentation with project sponsor; Completed; Mar 29/19. Project Management Deliverables: TO DO; PROGRESS; DUE DATE. Project Charter; Completed. Team Charter; Completed; Feb 7/19. WBS; Completed; Feb 15/19. Resourcing/HR Plan; Completed; Feb 15/19 Mar 3/19 Mar 8/19. Stakeholder Analysis; Completed; Feb 22/19 Mar 10/19 Mar 8/19. Requirements and Acceptance Criteria; Completed; Feb 22/19 Mar 10/19 Mar 22/19. Risk Analysis; Completed; Mar 8/19 Mar 10/19 Mar 22/19. Communication Plan; Completed; Mar 15/19. Issue Log; In Progress; Mar 29/19. Report for PH; In Progress; Mar 20/19 Mar 28/19. Project Assessment; Not Started; Apr 5/19. Project Plan Presentation; In Progress; Apr 11/19 Mar 28/19.

RISKS & ISSUES

- Final presentation still in draft stage – needs to be completed by Tuesday March 26th to review and practice. - Lists of strategies have not been completed. - Final report to give to sponsor is not completed.