DATE March 14, 2019

PARTICIPATION HOUSE - STATUS REPORT

| Project Name: | Participation House |
| --- | --- |
| Prepared By: | Participation House Project Managers |
| Subject: | Status Report |
| Period Ending: | March 15, 2019 |
| Self-Assessment: | Yellow |

KEY POINTS

- Progress thus far includes completion of Stakeholder Analysis, Risk Analysis, and Communication Plan. - Lists of potential organizations for Participation House to partner with have been created. - Lists of recruitment and marketing strategies need to be compiled.

PRIORITY

- Project Management documents currently need attention from both project managers. - Recruitment and marketing strategies lists need to be created and attached to Microsoft Teams.

MILESTONES

- Final meeting, prior to presentation, confirmed – March 21st at 11am. - Final project presentation date at Participation House confirmed – attempting to reschedule to March 28th at UWO in PM class. Participation House Deliverables: TO DO; PROGRESS; DUE DATE. Organize final meeting with project sponsor; Completed; Mar 15/19. Organize final presentation with project sponsor; Completed; Mar 29/19. Project Management Deliverables: TO DO; PROGRESS; DUE DATE. Project Charter; Completed. Team Charter; Completed; Feb 7/19. WBS; Completed; Feb 15/19. Resourcing Plan/Project Schedule; In Progress; Feb 15/19 Mar 3/19 Mar 8/19 Mar 22/19. Stakeholder Analysis; Completed; Feb 22/19 Mar 10/19 Mar 8/19. Requirements and Acceptance Criteria; In Progress; Feb 22/19 Mar 10/19 Mar 22/19. Risk Analysis; Completed; Mar 8/19 Mar 10/19 Mar 14/19. Communication Plan; Completed; Mar 15/19. Issue Log; In Progress; Mar 29/19. Report for PH; Not Started; Mar 20/19. Final Presentation for PH; Not Started; Mar 29/19. Project Assessment; Not Started; Apr 5/19. Project Plan Presentation; Not Started; Apr 11/19 Mar 28/19.

RISKS & ISSUES

- Delay in creation of project plan presentation. - High volume of documents still needs to be completed.