## Matrix
RACI Matrix | [5 empty] | Roles and Responsibilities
Participation House |  |  | Responsible, Accountable, Consulted, Informed
|  | ROLES | Sponsor: Donnie Antony | Project Manager: Sydney Mensen | Project Manager: Teresa Turnbull | Consultant: Jason Reed
| Deliverable or Task | Status | Sponsor / Leadership | Project Team |  | Other Resources
Investigation of Supply
| Contact career services |  | C/I | A | R | C
| Discuss opportunities |  | C/I | A | R | C
| Provide PH contact information |  | C/I | R | A
Investigation of Recruitment Strategies
| Research of tactics |  | C/I | A | R
| Report compilation of strongest tactics |  | C/I | A | R
Investigation of Marketing Strategies
| Research of strategies |  | C/I | R | A
| List composition of various strategies |  | C/I | R | A
Present Findings
| Complete report for Participation House |  | I | R | A | C
| Project Plan presentation for PM |  | I | R+A | R+A | C
| Project Plan submission |  | I | R+A | R+A | C
R | Responsible | Assigned to complete the task or deliverable.
A | Accountable | Has final decision-making authority and accountability for completion.
C | Consulted | An adviser, stakeholder, or subject matter expert who is consulted before a decision or action.
I | Informed | Must be informed after a decision or action.
R+A | Responsible + Accountable | Equally responsible and accountable.
C/I | Consulted +/ Informed | An adviser, stakeholder, or subject matter expert who is consulted AND/OR informed on a decision or action.