## Stakeholder Analysis
Stakeholder Analysis Template
|  | Stakeholder Type |  |  |  | Stakeholder Impact
Group | Key Representative | Accountable | Responsible | Consulted | Informed | Internal/External | Priority (High/ Med/ Low) | Direct/Indirect Involvement | Relationship with / Interest in project | Goals / Success Criteria | Impact on Project | What does the project need from this group? | Impact of Project | Potential Issues or Concerns | Needs | Management Strategy / Method of Communication
Participation House | Donnie Antony | NA | YES | YES | b | Internal | High | Direct | Project Owner | On time, to satisfaction | Over-all control, online access to documents, approval of deliverable | Direction. Approval | Future acquisition of potential hirables | Sources of hirables do not meet client needs. Hirables require excess levels of training. | Deliverable of list of sources for hirables | Review meeting, online access to Microsoft Teams
Western University Project Management Professor | Jason Reed | NA | NA | YES | b | External Auditor | Med | Direct | Professor & Auditor | Project Owner satisfied, students meet course objectives | Weekly review online | Direction. Support. | Review. Documentation. | Project management students do not complete deliverables or other essential documentation. | Every other week class-meetings. To be kept informed of all developments. | Online access to Microsoft Teams, in-person class-meetings
Participation House-Clients/Family | NA | NA | NA | NA | NA | External | Low | Indirect | Receiver of service | More services available | NA | NA | NA | NA | NA | NA
Learning Institutions | NA | NA | NA | NA | NA | External | Low | Indirect | Source of co-ops/student placements | Students have access to co-ops | NA | NA | NA | NA | NA | NA