DATE April 4, 2019

PARTICIPATION HOUSE - STATUS REPORT

| Project Name: | Participation House |
| --- | --- |
| Prepared By: | Participation House Project Managers |
| Subject: | Status Report |
| Period Ending: | April 5, 2019 |
| Self-Assessment: | Green |

KEY POINTS

- There are 2 project managers: Sydney Mensen and Teresa Turnbull. - All required PM documents have been completed. - Final report has been given to the project sponsor.

PRIORITY

- Submission of project management documents prior to April 11th, 2019.

MILESTONES

- Presentation was completed. - Final report was submitted to project sponsor. Participation House Deliverables: TO DO; PROGRESS; DUE DATE. Organize final meeting with project sponsor; Completed; Mar 15/19. Organize final presentation with project sponsor; Completed; Mar 29/19. Project Management Deliverables: TO DO; PROGRESS; DUE DATE. Project Charter; Completed. Team Charter; Completed; Feb 7/19. WBS; Completed; Feb 15/19. Resourcing/HR Plan; Completed; Feb 15/19 Mar 3/19 Mar 8/19. Stakeholder Analysis; Completed; Feb 22/19 Mar 10/19 Mar 8/19. Requirements and Acceptance Criteria; Completed; Feb 22/19 Mar 10/19 Mar 22/19. Risk Analysis; Completed; Mar 8/19 Mar 10/19 Mar 22/19. Communication Plan; Completed; Mar 15/19. Issue Log; Completed; Mar 29/19. Report for PH; Completed; Mar 20/19 Mar 28/19. Project Assessment; Completed; Apr 5/19. Project Plan Presentation; Completed; Apr 11/19 Mar 28/19.

RISKS & ISSUES

- None!