DATE March 8, 2019

PARTICIPATION HOUSE - STATUS REPORT

| Project Name: | Participation House |
| --- | --- |
| Prepared By: | Participation House Project Managers |
| Subject: | Status Report |
| Period Ending: | March 8, 2019 |
| Self-Assessment: | Yellow |

KEY POINTS

- There are 2 project managers: Sydney Mensen and Teresa Turnbull. - Progress thus far includes completion of Project Charter, Team Charter, and WBS. Lists of potential organizations for Participation House to partner with are being compiled currently, along with lists of resources and marketing strategies.

PRIORITY

- Project Management documents currently need attention from both project managers. - The lists need to be completed by both project managers and attached to Microsoft Teams.

MILESTONES

- Team Charter, Project Charter, and WBS have been completed. - Midway meeting, confirming final project, completed. - Final meeting, prior to presentation, confirmed. - Final project presentation date at Participation House confirmed. Participation House Deliverables: TO DO; PROGRESS; DUE DATE. Organize final meeting with project sponsor; Completed; Mar 15/19. Organize final presentation with project sponsor; Completed; Mar 29/19. Project Management Deliverables: TO DO; PROGRESS; DUE DATE. Project Charter; Completed. Team Charter; Completed; Feb 7/19. WBS; Completed; Feb 15/19. Resourcing/HR Plan; In Progress; Feb 15/19 Mar 3/19 Mar 8/19. Stakeholder Analysis; Completed; Feb 22/19 Mar 10/19. Requirements and Acceptance Criteria; In Progress; Feb 22/19 Mar 10/19. Risk Analysis; In Progress; Mar 8/19 Mar 10/19. Communication Plan; In Progress; Mar 15/19. Issue Log; In Progress; Mar 29/19. Report for PH; Not Started; Mar 20/19 Mar 21/19. Draft of Final Presentation for PH; Not Started; Mar 21/19. Final Presentation for PH; Not Started; Mar 29/19. Project Assessment; Not Started; Apr 5/19. Project Plan Presentation; Not Started; Apr 11/19.

RISKS & ISSUES

- Delay in completion of more PM documents. - Delay in meeting between the two Project Managers to complete the documents. - Draft of final presentation and report have not been started.